# Agent Wallet Project Brief

Initial implementation and security plan

Purpose. Build a testnet ERC-4337 smart account for AI agents whose target, recipient, session, gas, and USD spending policies are enforced on-chain. The first release must preserve a useful payment flow while stopping prompt injection, leaked-key abuse, calldata tricks, and cross-chain replay.

The critical delivery decision is to land one working Base Sepolia UserOperation by hour 6, complete policy enforcement by hour 12, freeze contracts by hour 16, and reserve the final eight hours for security evidence, rehearsal, and submission.

# Build Outcome

Agent buys API credits and an on-chain ticket through EntryPoint v0.7.

On-chain policy rejects non-allowlisted calls and decoded token recipients or spenders.

Over-limit, unknown-token, and stale-price requests become non-executing pending requests.

Owner controls policy, pause, revoke, approve, and reject through MetaMask.

Every demo claim maps to an automated test and inspectable testnet evidence.

# Locked Decisions

| Area | Decision | Reason |
| --- | --- | --- |
| Wallet | Custom IAccount with OpenZeppelin cryptographic utilities | Demonstrates the ERC-4337 boundary without hand-rolled signature code |
| EntryPoint | v0.7 PackedUserOperation | Matches the selected Base Sepolia bundler path |
| Network | Base Sepolia; Ethereum Sepolia for replay | Cheap execution and a concrete cross-chain negative test |
| Owner | MetaMask EOA | Reliable admin and approval flow for the first demo |
| Agent | Local 7-8B model plus scripted fallback | Keeps the agent local while making the stage path repeatable |
| Stack | Foundry, FastAPI, React, Vite, wagmi | Separates contracts, UserOperation services, and owner UX |
| Status | Testnet only and unaudited | Accurately describes the prototype's assurance level |

# System Architecture

The local agent and a direct attacker both submit through the bundler and EntryPoint, so neither can bypass wallet validation. The backend prepares operations and indexes events but is not a security boundary. The wallet performs structural checks during validation and performs oracle-dependent USD checks during execution.

| Component | Responsibility |
| --- | --- |
| AgentWallet | Validation, execution, allowlists, session checks, USD limits, pending approvals, owner controls, and EIP-1271 behavior |
| Factory | CREATE2 deployment and counterfactual wallet address |
| PriceOracle | Chainlink USD conversion, feed-specific staleness, and labeled testnet mock feed |
| Backend | UserOperation builder and sender, event indexer, paywall, and push notification sender |
| Dashboard | Policy editor, activity feed, pending approvals, pause and revoke, and attack console |
| Demo targets | Ticket purchase and HTTP 402-style API purchase |

# Contract Policy

## Validation

Accept validation only from the EntryPoint and recover the signer from userOpHash.

Allow a valid owner signature full access; require an active and unrevoked session for the agent.

Permit only execute and executeBatch for agent operations; reject self-calls, admin paths, and delegatecall.

Check each inner target and selector, then decode token transfers and approvals to check the real recipient or spender.

Cap agent gas and fee fields and pack session times into validationData.

## Execution

Decode and price the complete batch before making an external call.

Count native value, token transfers, and the full approved amount toward the USD total.

Execute and update the fixed daily counter only when every check passes.

Record a capped pending request without execution when the limit is exceeded or pricing fails.

Allow only the owner to execute or reject a non-expired pending request.

# Security Evidence

| Attack | Expected result | Evidence |
| --- | --- | --- |
| Leaked agent key | Non-allowlisted call rejected in validation | Raw-key attack script and unit test |
| Approve attacker | Decoded spender rejected | Token calldata test and live attack |
| Hidden recipient | Decoded recipient rejected | Crafted transfer test and live attack |
| Split batch | Total exceeds policy and becomes pending | Batch aggregation test |
| Admin self-call | Rejected before execution | Selector and self-call tests |
| Cross-chain replay | Signature or hash mismatch | Same signed payload on Ethereum Sepolia |
| Expired or revoked session | Rejected by validity or session state | Boundary tests |
| Permit signature | Agent EIP-1271 request returns invalid | Signature-path test |
| Stale price | Pending only; never automatic execution | Mock-feed test |
| Gas grief | Oversized fields rejected | Gas-cap tests |

# Delivery Gates

| Gate | Deadline | Pass condition |
| --- | --- | --- |
| First UserOperation | Hour 6 | Owner operation executes through a Base Sepolia bundler |
| Policy complete | Hour 12 | Sessions, allowlists, USD limits, pending queue, pause, and revoke pass on testnet |
| Contract freeze | Hour 16 | Verified deployments and acceptable unit, fuzz, invariant, and static-analysis results |
| Demo freeze | Hour 20 | Happy path, four attack categories, owner approval, explorer evidence, and backup video work |
| Submission | Hour 24 | Public URLs, documentation, scripts, deck, and final assets are complete |

# Team Ownership

| Role | Owns | Handoff |
| --- | --- | --- |
| A Contract lead | Wallet, factory, validation, execution, deployments | B for tests; C for ABIs |
| B Security and tests | Unit, fuzz, invariants, Slither, attacks, threat model | A for fixes; D for console |
| C Agent and backend | Local agent, tools, UserOperation sender, indexer, paywall, push | D for APIs; B for attacker bot |
| D Frontend, UX, pitch | Dashboard, MetaMask flow, PWA, attack console, README, deck | Whole team for rehearsal |

# Risks and Recovery

| Risk | Early warning | Recovery |
| --- | --- | --- |
| Bundler integration | No UserOperation by hour 6 | Inspect simulateValidation and switch to the backup provider |
| Encoding mismatch | Hash or signature errors | Use EntryPoint getUserOpHash rather than duplicating hashing |
| Missing token feed | Unsupported token found in setup | Use a clearly labeled owner-set testnet mock feed |
| Web push | Phone test fails by hour 12 | Use Android Chrome and an in-dashboard notification fallback |
| Local model | Tool arguments fail in rehearsal | Constrain JSON schemas and switch to the scripted agent |
| Late contract bug | Invariant fails after hour 16 | Fix, redeploy, update the environment address, and rerun the full suite |
| Stage network | RPC or Wi-Fi stalls | Use a hotspot or play the local hour-20 backup video |

# Known Limitations

The wallet is unaudited and restricted to testnet.

The fixed daily window can allow up to twice the nominal limit around a reset boundary.

A compromised session key may spend within its valid policy until it expires or is revoked.

Validation failures are not durable on-chain events; the dashboard must source them from bundler simulation or backend telemetry.

Full x402 support may conflict with the decision to reject arbitrary agent EIP-1271 signatures.

# Immediate Next Actions

1. Confirm EntryPoint, bundler, RPC, Chainlink feed, and heartbeat values for Base Sepolia.

2. Scaffold the repository and add a secret-free environment example.

3. Write interface-first security tests before completing wallet logic.

4. Land and record the first owner UserOperation.

5. Keep the architecture, threat model, build plan, and demo runbook updated as executable decisions change.

# Configuration Record

Complete these fields as soon as the first deployment path is confirmed.

| Value | Current state |
| --- | --- |
| Base Sepolia EntryPoint | TBD |
| Bundler and backup provider | TBD |
| Factory and wallet addresses | TBD |
| Token feeds and heartbeat thresholds | TBD |
| Dashboard and backend URLs | TBD |
| Demo UserOperation and explorer links | TBD |

# Submission Checklist

Verified contract addresses and deployment commit are recorded.

Public dashboard and backend work from a device outside the development laptop.

CI, fuzz tests, invariants, and Slither evidence are ready to show.

Each attack script runs with one command and has a matching automated test.

The three-minute backup video is available offline.

The interface clearly displays Testnet only - unaudited.